## BIM_DATA
ID | Title | Status | Category | Type | Description | Assigned to | Company | Watchers | Created by | Created on | Due date | Start date | Location | Location details | Placement | Root cause | Published | Updated by | Updated on | Closed by | Closed at | Comments | Month
#1 | Concrete-Rectangular-Column1 [542964/422790] and Pipe [616663] | Closed | Coordination | Clash | 1 total clashes: 1 clash between Basic Wall [344561] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} | Jeffy George MCEM4001 - ICT | MCEM4001 - ICT | Kartik Dalwadi | Shyam Chandresha | 2025-07-21 00:00:00 |  |  |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Shyam Chandresha | 2025-07-25 00:00:00 | Tanay Trivedi | 2025-08-18 00:00:00 |  | 7
#2 | 4 clashes across 1 Clash Groups | Closed | Coordination | Clash | 4 total clashes: 1 clash between Pipe [650707] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Duct [780331] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Floor [311390] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Structural Framing [540568] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} |  |  | Tanay Trivedi, Kartik Dalwadi | Jeffy George MCEM4001 - ICT | 2025-07-28 00:00:00 | 2025-08-06 | 2025-07-28 |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Kartik Dalwadi | 2025-08-01 00:00:00 | Shyam Chandresha | 2025-08-27 00:00:00 |  | 7
#3 | 3 clashes across 2 Clash Groups | Closed | Coordination | Clash | 3 total clashes: 1 clash between Duct [709842] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Floor [483977] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [559680/566455] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} |  |  | Tanay Trivedi, Kartik Dalwadi, Jeffy George MCEM4001 - ICT | Shyam Chandresha | 2025-07-25 00:00:00 | 2025-08-04 |  |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Shyam Chandresha | 2025-07-31 00:00:00 | Shyam Chandresha | 2025-08-01 00:00:00 |  | 7
#4 | Ramp [548682/482490] and Ramp [530870/503712] | Open | Coordination | Clash | 1 total clashes: 1 clash between Structural Framing [437452] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} |  |  | Kartik Dalwadi, Tanay Trivedi | Tanay Trivedi | 2025-07-02 00:00:00 |  | 2025-07-02 |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Shyam Chandresha | 2025-07-09 00:00:00 |  |  |  | 7
#5 | Concrete-Rectangular Beam1 [564481] and Concrete-Rectangular Beam1 [510666] | Open | Coordination | Clash | 1 total clashes: 1 clash between Concrete-Rectangular-Column1 [500864/500039] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} | Jeffy George MCEM4001 - ICT | MCEM4001 - ICT |  | Kartik Dalwadi | 2025-07-05 00:00:00 | 2025-08-02 |  |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Tanay Trivedi | 2025-07-14 00:00:00 |  |  |  | 7
#6 | 10 clashes across 6 Clash Groups | Closed | Coordination | Clash | 10 total clashes: 1 clash between Basic Wall [477009] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Duct [856170] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Basic Wall [349325] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Duct [761225] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Ramp [415184/463143] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} | Jeffy George MCEM4001 - ICT | MCEM4001 - ICT | Shyam Chandresha | Jeffy George MCEM4001 - ICT | 2025-07-14 00:00:00 | 2025-07-31 |  |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-07-22 00:00:00 | Tanay Trivedi | 2025-07-19 00:00:00 |  | 7
#7 | 50 clashes across 49 Clash Groups | Open | Coordination | Clash | 50 total clashes: 1 clash between Structural Framing [431720] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Ramp [458903/416784] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Duct [611028] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Ramp [554256/457728] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Basic Wall [338610] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} |  |  |  | Jeffy George MCEM4001 - ICT | 2025-07-28 00:00:00 |  |  |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Shyam Chandresha | 2025-08-03 00:00:00 |  |  |  | 7
#8 | 36 clashes across 32 Clash Groups | Open | Coordination | Clash | 36 total clashes: 1 clash between Concrete-Rectangular-Column1 [425409/512997] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Duct [822077] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Pipe [844855] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Basic Wall [496518] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [415889/505544] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} |  |  | Kartik Dalwadi | Tanay Trivedi | 2025-07-22 00:00:00 |  |  |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-07-25 00:00:00 |  |  |  | 7
#9 | 50 clashes across 46 Clash Groups | Open | Coordination | Clash | 50 total clashes: 1 clash between Concrete-Rectangular Beam1 [506539] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Structural Framing [526185] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Ramp [505130/415370] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [499345] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Basic Wall [422346] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} |  |  | Shyam Chandresha, Jeffy George MCEM4001 - ICT, Kartik Dalwadi | Tanay Trivedi | 2025-07-08 00:00:00 | 2025-08-21 | 2025-07-08 |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Kartik Dalwadi | 2025-07-12 00:00:00 |  |  |  | 7
#10 | 12 clashes across 11 Clash Groups | Open | Coordination | Clash | 12 total clashes: 1 clash between Concrete-Rectangular-Column1 [448712/417962] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [461657/505847] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [549336/464543] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Basic Wall [482367] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [509897/553006] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} |  |  | Shyam Chandresha, Kartik Dalwadi | Tanay Trivedi | 2025-07-02 00:00:00 |  | 2025-07-02 |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Tanay Trivedi | 2025-07-09 00:00:00 |  |  |  | 7
#11 | 12 clashes across 8 Clash Groups | Closed | Coordination | Clash | 12 total clashes: 1 clash between Duct [636066] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Ramp [496869/474707] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [514867] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Floor [460347] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Basic Wall [495076] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT, Kartik Dalwadi | Tanay Trivedi | 2025-07-15 00:00:00 |  |  |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-07-24 00:00:00 | Jeffy George MCEM4001 - ICT | 2025-08-13 00:00:00 |  | 7
#12 | 10 clashes across 10 Clash Groups | Open | Coordination | Clash | 10 total clashes: 1 clash between Pipe [745060] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Basic Wall [320929] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Duct [668587] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Floor [342357] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Structural Framing [544619] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} |  |  | Jeffy George MCEM4001 - ICT | Kartik Dalwadi | 2025-07-07 00:00:00 | 2025-07-23 |  |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-07-13 00:00:00 |  |  |  | 7
#13 | 24 clashes across 20 Clash Groups | Closed | Coordination | Clash | 24 total clashes: 1 clash between Concrete-Rectangular Beam1 [446413] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Pipe [612995] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [487080] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Pipe [730111] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Floor [341732] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Shyam Chandresha | Jeffy George MCEM4001 - ICT | 2025-08-02 00:00:00 |  | 2025-08-02 |  |  | CEPT-ICP-M1-STR-MD-19092025.rvt |  | Published | Kartik Dalwadi | 2025-08-10 00:00:00 | Jeffy George MCEM4001 - ICT | 2025-09-01 00:00:00 |  | 8
#14 | 3 clashes across 2 Clash Groups | Closed | Coordination | Clash | 3 total clashes: 1 clash between Basic Wall [350236] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Floor [346810] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Floor [310028] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT, Shyam Chandresha, Kartik Dalwadi | Jeffy George MCEM4001 - ICT | 2025-08-28 00:00:00 |  |  |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Kartik Dalwadi | 2025-09-02 00:00:00 | Shyam Chandresha | 2025-09-02 00:00:00 |  | 8
#15 | 4 clashes across 1 Clash Groups | Open | Coordination | Clash | 4 total clashes: 1 clash between Floor [432939] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Floor [474821] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Pipe [771013] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Pipe [755008] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Tanay Trivedi | Shyam Chandresha | 2025-08-17 00:00:00 | 2025-08-24 |  |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Shyam Chandresha | 2025-08-24 00:00:00 |  |  |  | 8
#16 | 24 clashes across 24 Clash Groups | Open | Coordination | Clash | 24 total clashes: 1 clash between Ramp [534001/524042] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [422228] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Floor [435122] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Duct [648961] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Ramp [481374/458888] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} |  |  | Kartik Dalwadi | Shyam Chandresha | 2025-08-07 00:00:00 | 2025-08-18 |  |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Shyam Chandresha | 2025-08-17 00:00:00 |  |  |  | 8
#17 | 6 clashes across 1 Clash Groups | Open | Coordination | Clash | 6 total clashes: 1 clash between Pipe [714735] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [535779] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Structural Framing [413164] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Ramp [431813/519658] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [521803] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Shyam Chandresha, Tanay Trivedi, Kartik Dalwadi | Tanay Trivedi | 2025-08-21 00:00:00 |  |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Kartik Dalwadi | 2025-08-29 00:00:00 |  |  |  | 8
#18 | 3 clashes across 2 Clash Groups | Closed | Coordination | Clash | 3 total clashes: 1 clash between Duct [767619] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [436273/439539] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Ramp [500410/440056] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT | Kartik Dalwadi, Jeffy George MCEM4001 - ICT, Tanay Trivedi | Shyam Chandresha | 2025-08-21 00:00:00 |  | 2025-08-21 |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-08-28 00:00:00 | Kartik Dalwadi | 2025-09-19 00:00:00 |  | 8
#19 | 4 clashes across 2 Clash Groups | Closed | Coordination | Clash | 4 total clashes: 1 clash between Structural Framing [457520] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Floor [414251] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Structural Framing [407608] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Pipe [776228] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT |  | Kartik Dalwadi | 2025-08-23 00:00:00 | 2025-08-31 |  |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Shyam Chandresha | 2025-08-30 00:00:00 | Kartik Dalwadi | 2025-09-21 00:00:00 |  | 8
#20 | 5 clashes across 3 Clash Groups | Closed | Coordination | Clash | 5 total clashes: 1 clash between Pipe [745886] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Pipe [732262] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [523288/405081] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Basic Wall [569540] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Duct [717556] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT | Jeffy George MCEM4001 - ICT | 2025-08-14 00:00:00 |  |  |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-08-24 00:00:00 | Shyam Chandresha | 2025-09-02 00:00:00 |  | 8
#21 | 50 clashes across 45 Clash Groups | Closed | Coordination | Clash | 50 total clashes: 1 clash between Basic Wall [563502] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Floor [450941] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Pipe [807961] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Ramp [419922/555214] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Ramp [426712/479058] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT, Tanay Trivedi | Jeffy George MCEM4001 - ICT | 2025-08-22 00:00:00 |  |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-08-28 00:00:00 | Kartik Dalwadi | 2025-09-02 00:00:00 |  | 8
#22 | 5 clashes across 5 Clash Groups | Closed | Coordination | Clash | 5 total clashes: 1 clash between Structural Framing [521863] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Pipe [740716] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Duct [728710] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [473119/518175] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Ramp [521820/549382] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} |  |  | Shyam Chandresha, Kartik Dalwadi | Kartik Dalwadi | 2025-08-16 00:00:00 |  |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Tanay Trivedi | 2025-08-20 00:00:00 | Kartik Dalwadi | 2025-09-01 00:00:00 |  | 8
#23 | 10 clashes across 10 Clash Groups | Open | Coordination | Clash | 10 total clashes: 1 clash between Pipe [856155] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Ramp [524804/569319] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Structural Framing [517486] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Basic Wall [344393] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Floor [358090] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT | Tanay Trivedi, Shyam Chandresha, Kartik Dalwadi | Kartik Dalwadi | 2025-08-09 00:00:00 | 2025-09-02 |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Shyam Chandresha | 2025-08-15 00:00:00 |  |  |  | 8
#24 | 50 clashes across 50 Clash Groups | Closed | Coordination | Clash | 50 total clashes: 1 clash between Floor [326352] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Ramp [477659/459633] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Duct [694079] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Floor [303708] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [471909] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT, Kartik Dalwadi, Shyam Chandresha | Jeffy George MCEM4001 - ICT | 2025-08-08 00:00:00 |  |  |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-08-16 00:00:00 | Tanay Trivedi | 2025-08-19 00:00:00 |  | 8
#25 | 6 clashes across 2 Clash Groups | Closed | Coordination | Clash | 6 total clashes: 1 clash between Floor [322329] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Ramp [431051/546295] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Pipe [718325] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Pipe [836199] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Structural Framing [477949] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} | Jeffy George MCEM4001 - ICT | MCEM4001 - ICT |  | Kartik Dalwadi | 2025-08-02 00:00:00 | 2025-08-25 | 2025-08-02 |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Tanay Trivedi | 2025-08-06 00:00:00 | Jeffy George MCEM4001 - ICT | 2025-08-22 00:00:00 |  | 8
#26 | 5 clashes across 1 Clash Groups | Closed | Coordination | Clash | 5 total clashes: 1 clash between Ramp [475524/474112] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Structural Framing [418659] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Ramp [469351/563855] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Ramp [511447/430087] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Ramp [569773/439056] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} |  |  | Tanay Trivedi | Tanay Trivedi | 2025-08-06 00:00:00 | 2025-09-18 | 2025-08-06 |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Shyam Chandresha | 2025-08-16 00:00:00 | Jeffy George MCEM4001 - ICT | 2025-08-28 00:00:00 |  | 8
#27 | 3 clashes across 2 Clash Groups | Closed | Coordination | Clash | 3 total clashes: 1 clash between Duct [731264] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Basic Wall [343940] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Ramp [550784/553910] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Kartik Dalwadi, Shyam Chandresha, Jeffy George MCEM4001 - ICT | Jeffy George MCEM4001 - ICT | 2025-09-15 00:00:00 |  | 2025-09-15 |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Tanay Trivedi | 2025-09-25 00:00:00 | Tanay Trivedi | 2025-10-12 00:00:00 |  | 9
#28 | 4 clashes across 3 Clash Groups | Open | Coordination | Clash | 4 total clashes: 1 clash between Pipe [888409] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Basic Wall [439229] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [482448/466164] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Duct [660776] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT, Kartik Dalwadi, Shyam Chandresha | Kartik Dalwadi | 2025-09-03 00:00:00 | 2025-10-08 | 2025-09-03 |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-09-13 00:00:00 |  |  |  | 9
#29 | Basic Wall [485156] and Ramp [441517/481461] | Closed | Coordination | Clash | 1 total clashes: 1 clash between Basic Wall [464769] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} |  |  |  | Kartik Dalwadi | 2025-09-07 00:00:00 | 2025-09-23 |  |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-09-15 00:00:00 | Tanay Trivedi | 2025-09-16 00:00:00 |  | 9
#30 | 6 clashes across 2 Clash Groups | Closed | Coordination | Clash | 6 total clashes: 1 clash between Concrete-Rectangular Beam1 [418300] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Floor [408774] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Duct [866200] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Floor [300672] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Floor [490329] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Tanay Trivedi, Shyam Chandresha, Kartik Dalwadi | Tanay Trivedi | 2025-09-23 00:00:00 | 2025-10-12 | 2025-09-23 |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Kartik Dalwadi | 2025-10-01 00:00:00 | Tanay Trivedi | 2025-10-20 00:00:00 |  | 9
#31 | Duct [847975] and Pipe [802416] | Open | Coordination | Clash | 1 total clashes: 1 clash between Concrete-Rectangular Beam1 [529847] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT |  | Jeffy George MCEM4001 - ICT | 2025-09-08 00:00:00 |  | 2025-09-08 |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Shyam Chandresha | 2025-09-16 00:00:00 |  |  |  | 9
#32 | Structural Framing [469474] and Duct [808395] | Open | Coordination | Clash | 1 total clashes: 1 clash between Concrete-Rectangular-Column1 [486131/539885] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT |  | Kartik Dalwadi | 2025-09-01 00:00:00 |  | 2025-09-01 |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Tanay Trivedi | 2025-09-11 00:00:00 |  |  |  | 9
#33 | 5 clashes across 3 Clash Groups | Open | Coordination | Clash | 5 total clashes: 1 clash between Basic Wall [332056] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Duct [629422] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Floor [393969] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Duct [825803] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [464014] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} |  |  |  | Kartik Dalwadi | 2025-09-10 00:00:00 | 2025-10-02 |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Shyam Chandresha | 2025-09-20 00:00:00 |  |  |  | 9
#34 | 24 clashes across 24 Clash Groups | Closed | Coordination | Clash | 24 total clashes: 1 clash between Concrete-Rectangular Beam1 [419362] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Structural Framing [490587] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Floor [467493] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Pipe [731123] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Structural Framing [479199] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Jeffy George MCEM4001 - ICT | MCEM4001 - ICT | Kartik Dalwadi | Shyam Chandresha | 2025-09-19 00:00:00 |  |  |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Kartik Dalwadi | 2025-09-29 00:00:00 | Tanay Trivedi | 2025-10-08 00:00:00 |  | 9
#35 | 12 clashes across 8 Clash Groups | Closed | Coordination | Clash | 12 total clashes: 1 clash between Duct [714821] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Ramp [562762/465700] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [564691] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [564484/569434] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Basic Wall [400984] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT |  | Kartik Dalwadi | 2025-09-23 00:00:00 |  |  |  |  | CEPT-ICP-M1-STR-MD-19092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-09-28 00:00:00 | Kartik Dalwadi | 2025-10-19 00:00:00 |  | 9
#36 | 3 clashes across 3 Clash Groups | Closed | Coordination | Clash | 3 total clashes: 1 clash between Duct [660382] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Structural Framing [419739] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [459143] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} |  |  | Jeffy George MCEM4001 - ICT, Shyam Chandresha, Kartik Dalwadi | Kartik Dalwadi | 2025-09-07 00:00:00 |  | 2025-09-07 |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Tanay Trivedi | 2025-09-15 00:00:00 | Tanay Trivedi | 2025-09-29 00:00:00 |  | 9
#37 | Ramp [523594/406560] and Duct [716060] | Open | Coordination | Clash | 1 total clashes: 1 clash between Concrete-Rectangular-Column1 [566567/521704] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} |  |  |  | Tanay Trivedi | 2025-09-09 00:00:00 |  |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Kartik Dalwadi | 2025-09-10 00:00:00 |  |  |  | 9
#38 | 4 clashes across 4 Clash Groups | Closed | Coordination | Clash | 4 total clashes: 1 clash between Pipe [746664] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Basic Wall [500952] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Duct [713911] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Structural Framing [516574] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} |  |  | Tanay Trivedi, Jeffy George MCEM4001 - ICT | Shyam Chandresha | 2025-09-04 00:00:00 |  | 2025-09-04 |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Tanay Trivedi | 2025-09-11 00:00:00 | Shyam Chandresha | 2025-09-26 00:00:00 |  | 9
#39 | 24 clashes across 20 Clash Groups | Open | Coordination | Clash | 24 total clashes: 1 clash between Ramp [417985/545282] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Ramp [553716/456610] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Ramp [486129/438680] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Basic Wall [392685] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [434076] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} |  |  |  | Tanay Trivedi | 2025-09-28 00:00:00 |  | 2025-09-28 |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Shyam Chandresha | 2025-10-01 00:00:00 |  |  |  | 9
#40 | 3 clashes across 1 Clash Groups | Open | Coordination | Clash | 3 total clashes: 1 clash between Concrete-Rectangular-Column1 [524845/517512] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Duct [869084] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [518490/532078] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT, Kartik Dalwadi, Shyam Chandresha | Shyam Chandresha | 2025-09-08 00:00:00 |  |  |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-09-15 00:00:00 |  |  |  | 9
#41 | 4 clashes across 3 Clash Groups | Open | Coordination | Clash | 4 total clashes: 1 clash between Pipe [878164] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Floor [418938] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Pipe [651998] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [544529/456367] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Kartik Dalwadi, Shyam Chandresha | Kartik Dalwadi | 2025-09-23 00:00:00 | 2025-10-20 |  |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Kartik Dalwadi | 2025-09-30 00:00:00 |  |  |  | 9
#42 | Concrete-Rectangular-Column1 [513213/425313] and Duct [668217] | Closed | Coordination | Clash | 1 total clashes: 1 clash between Basic Wall [473738] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT |  | Tanay Trivedi | 2025-09-22 00:00:00 | 2025-10-21 |  |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-09-27 00:00:00 | Kartik Dalwadi | 2025-10-01 00:00:00 |  | 9
#43 | 4 clashes across 2 Clash Groups | Closed | Coordination | Clash | 4 total clashes: 1 clash between Pipe [894107] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Basic Wall [479644] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Floor [307589] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [471636] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Kartik Dalwadi | Tanay Trivedi | 2025-09-17 00:00:00 |  | 2025-09-17 |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Tanay Trivedi | 2025-09-19 00:00:00 | Kartik Dalwadi | 2025-10-13 00:00:00 |  | 9
#44 | 6 clashes across 6 Clash Groups | Closed | Coordination | Clash | 6 total clashes: 1 clash between Duct [897582] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [413791/440784] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [561962] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Basic Wall [496676] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [471330/516159] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Shyam Chandresha, Tanay Trivedi | Kartik Dalwadi | 2025-09-01 00:00:00 |  |  |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Kartik Dalwadi | 2025-09-03 00:00:00 | Shyam Chandresha | 2025-09-22 00:00:00 |  | 9
#45 | 24 clashes across 19 Clash Groups | Open | Coordination | Clash | 24 total clashes: 1 clash between Basic Wall [373588] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Floor [355373] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [466982] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Floor [386015] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [402026/530386] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} |  |  | Tanay Trivedi | Kartik Dalwadi | 2025-09-22 00:00:00 |  | 2025-09-22 |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Shyam Chandresha | 2025-09-24 00:00:00 |  |  |  | 9
#46 | 12 clashes across 10 Clash Groups | Closed | Coordination | Clash | 12 total clashes: 1 clash between Basic Wall [405136] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [562037] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Structural Framing [494857] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [514481/427751] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Ramp [514209/554369] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT | Shyam Chandresha, Kartik Dalwadi | Kartik Dalwadi | 2025-09-14 00:00:00 |  | 2025-09-14 |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-09-17 00:00:00 | Tanay Trivedi | 2025-09-21 00:00:00 |  | 9
#47 | 36 clashes across 32 Clash Groups | Open | Coordination | Clash | 36 total clashes: 1 clash between Concrete-Rectangular Beam1 [557915] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [419753] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [564613] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Structural Framing [521622] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Structural Framing [547978] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} |  |  |  | Tanay Trivedi | 2025-10-17 00:00:00 |  |  |  |  | CEPT-ICP-M1-STR-MD-19092025.rvt |  | Published | Tanay Trivedi | 2025-10-25 00:00:00 |  |  |  | 10
#48 | Floor [421043] and Structural Framing [409858] | Open | Coordination | Clash | 1 total clashes: 1 clash between Basic Wall [416662] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} | Jeffy George MCEM4001 - ICT | MCEM4001 - ICT | Kartik Dalwadi, Tanay Trivedi, Jeffy George MCEM4001 - ICT | Tanay Trivedi | 2025-10-09 00:00:00 | 2025-11-21 | 2025-10-09 |  |  | CEPT-ICP-M1-STR-MD-19092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-10-17 00:00:00 |  |  |  | 10
#49 | Structural Framing [427132] and Duct [644212] | Open | Coordination | Clash | 1 total clashes: 1 clash between Concrete-Rectangular Beam1 [410260] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Tanay Trivedi, Shyam Chandresha | Shyam Chandresha | 2025-10-11 00:00:00 |  |  |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Kartik Dalwadi | 2025-10-18 00:00:00 |  |  |  | 10
#50 | Pipe [748974] and Floor [489722] | Closed | Coordination | Clash | 1 total clashes: 1 clash between Concrete-Rectangular Beam1 [487388] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT | Shyam Chandresha, Tanay Trivedi, Jeffy George MCEM4001 - ICT | Jeffy George MCEM4001 - ICT | 2025-10-20 00:00:00 | 2025-11-17 | 2025-10-20 |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Shyam Chandresha | 2025-10-25 00:00:00 | Tanay Trivedi | 2025-11-14 00:00:00 |  | 10
#51 | Pipe [866594] and Duct [609558] | Open | Coordination | Clash | 1 total clashes: 1 clash between Duct [761934] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Shyam Chandresha | Shyam Chandresha | 2025-10-22 00:00:00 |  |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Shyam Chandresha | 2025-10-25 00:00:00 |  |  |  | 10
#52 | 50 clashes across 46 Clash Groups | Closed | Coordination | Clash | 50 total clashes: 1 clash between Concrete-Rectangular Beam1 [563771] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [514733] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Basic Wall [427704] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Duct [724534] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Structural Framing [560063] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} |  |  | Tanay Trivedi | Tanay Trivedi | 2025-10-26 00:00:00 | 2025-11-14 |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Kartik Dalwadi | 2025-11-03 00:00:00 | Jeffy George MCEM4001 - ICT | 2025-11-24 00:00:00 |  | 10
#53 | 50 clashes across 46 Clash Groups | Open | Coordination | Clash | 50 total clashes: 1 clash between Concrete-Rectangular Beam1 [465536] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Basic Wall [488081] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Structural Framing [497311] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [535242/432683] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Floor [321987] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT, Kartik Dalwadi, Shyam Chandresha | Shyam Chandresha | 2025-10-19 00:00:00 | 2025-11-21 |  |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Tanay Trivedi | 2025-10-25 00:00:00 |  |  |  | 10
#54 | 4 clashes across 2 Clash Groups | Open | Coordination | Clash | 4 total clashes: 1 clash between Basic Wall [395203] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Structural Framing [436383] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Structural Framing [517598] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Basic Wall [557465] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} |  |  | Kartik Dalwadi | Jeffy George MCEM4001 - ICT | 2025-10-17 00:00:00 | 2025-11-08 |  |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-10-19 00:00:00 |  |  |  | 10
#55 | 6 clashes across 4 Clash Groups | Closed | Coordination | Clash | 6 total clashes: 1 clash between Basic Wall [481168] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Duct [726124] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Pipe [698206] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [537228/494530] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [537903/542627] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} | Jeffy George MCEM4001 - ICT | MCEM4001 - ICT | Tanay Trivedi, Shyam Chandresha, Jeffy George MCEM4001 - ICT | Jeffy George MCEM4001 - ICT | 2025-10-02 00:00:00 | 2025-10-31 |  |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Kartik Dalwadi | 2025-10-08 00:00:00 | Kartik Dalwadi | 2025-10-27 00:00:00 |  | 10
#56 | Basic Wall [412353] and Duct [691797] | Open | Coordination | Clash | 1 total clashes: 1 clash between Structural Framing [525444] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} |  |  | Jeffy George MCEM4001 - ICT, Shyam Chandresha, Kartik Dalwadi | Shyam Chandresha | 2025-10-22 00:00:00 | 2025-10-31 |  |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Shyam Chandresha | 2025-10-23 00:00:00 |  |  |  | 10
#57 | 3 clashes across 1 Clash Groups | Open | Coordination | Clash | 3 total clashes: 1 clash between Duct [743244] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [496474/514544] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Pipe [830548] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Tanay Trivedi, Kartik Dalwadi, Shyam Chandresha | Kartik Dalwadi | 2025-10-10 00:00:00 | 2025-10-22 |  |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Tanay Trivedi | 2025-10-12 00:00:00 |  |  |  | 10
#58 | 4 clashes across 4 Clash Groups | Closed | Coordination | Clash | 4 total clashes: 1 clash between Concrete-Rectangular Beam1 [516367] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Duct [834424] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Basic Wall [510530] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Duct [828034] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} |  |  | Tanay Trivedi, Kartik Dalwadi, Jeffy George MCEM4001 - ICT | Tanay Trivedi | 2025-10-27 00:00:00 |  | 2025-10-27 |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-10-28 00:00:00 | Tanay Trivedi | 2025-11-10 00:00:00 |  | 10
#59 | 2 clashes across 1 Clash Groups | Open | Coordination | Clash | 2 total clashes: 1 clash between Concrete-Rectangular Beam1 [517944] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Duct [795042] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT | Tanay Trivedi, Kartik Dalwadi, Shyam Chandresha | Kartik Dalwadi | 2025-10-26 00:00:00 | 2025-11-03 | 2025-10-26 |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-10-30 00:00:00 |  |  |  | 10
#60 | 3 clashes across 3 Clash Groups | Open | Coordination | Clash | 3 total clashes: 1 clash between Floor [481922] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Structural Framing [452475] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [435580/419412] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT |  | Kartik Dalwadi | 2025-10-16 00:00:00 | 2025-10-27 | 2025-10-16 |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Shyam Chandresha | 2025-10-22 00:00:00 |  |  |  | 10
#61 | 50 clashes across 46 Clash Groups | Open | Coordination | Clash | 50 total clashes: 1 clash between Ramp [529504/406890] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Duct [890466] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Duct [845055] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [560418] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [417235/481078] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT |  | Kartik Dalwadi | 2025-10-10 00:00:00 | 2025-10-21 |  |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Kartik Dalwadi | 2025-10-13 00:00:00 |  |  |  | 10
#62 | 24 clashes across 19 Clash Groups | Open | Coordination | Clash | 24 total clashes: 1 clash between Concrete-Rectangular-Column1 [535817/440112] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Floor [343163] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [484583] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Ramp [490707/536025] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Floor [320672] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT | Tanay Trivedi | Tanay Trivedi | 2025-10-22 00:00:00 | 2025-11-30 | 2025-10-22 |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Shyam Chandresha | 2025-11-01 00:00:00 |  |  |  | 10
#63 | 24 clashes across 19 Clash Groups | Open | Coordination | Clash | 24 total clashes: 1 clash between Concrete-Rectangular-Column1 [411917/568153] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Floor [470689] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Ramp [549982/509205] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Basic Wall [450557] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Floor [468272] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} |  |  | Tanay Trivedi, Shyam Chandresha, Jeffy George MCEM4001 - ICT | Tanay Trivedi | 2025-10-19 00:00:00 |  |  |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Kartik Dalwadi | 2025-10-20 00:00:00 |  |  |  | 10
#64 | 36 clashes across 35 Clash Groups | Closed | Coordination | Clash | 36 total clashes: 1 clash between Concrete-Rectangular-Column1 [483654/463370] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Structural Framing [432118] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Floor [417858] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Ramp [436930/425378] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Basic Wall [396077] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} |  |  | Tanay Trivedi | Kartik Dalwadi | 2025-10-15 00:00:00 | 2025-11-03 | 2025-10-15 |  |  | CEPT-ICP-M1-STR-MD-19092025.rvt |  | Published | Kartik Dalwadi | 2025-10-25 00:00:00 | Shyam Chandresha | 2025-11-08 00:00:00 |  | 10
#65 | 3 clashes across 2 Clash Groups | Open | Coordination | Clash | 3 total clashes: 1 clash between Ramp [456398/552920] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Duct [625510] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Basic Wall [393755] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} |  |  |  | Kartik Dalwadi | 2025-10-16 00:00:00 |  | 2025-10-16 |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Kartik Dalwadi | 2025-10-18 00:00:00 |  |  |  | 10
#66 | Pipe [626821] and Ramp [495033/545024] | Open | Coordination | Clash | 1 total clashes: 1 clash between Floor [319275] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT |  | Kartik Dalwadi | 2025-10-24 00:00:00 | 2025-11-25 |  |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Kartik Dalwadi | 2025-10-27 00:00:00 |  |  |  | 10
#67 | 2 clashes across 1 Clash Groups | Open | Coordination | Clash | 2 total clashes: 1 clash between Concrete-Rectangular Beam1 [487304] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Structural Framing [536139] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Tanay Trivedi, Jeffy George MCEM4001 - ICT | Kartik Dalwadi | 2025-10-11 00:00:00 | 2025-11-06 | 2025-10-11 |  |  | CEPT-ICP-M1-STR-MD-19092025.rvt |  | Published | Shyam Chandresha | 2025-10-18 00:00:00 |  |  |  | 10
#68 | 36 clashes across 33 Clash Groups | Open | Coordination | Clash | 36 total clashes: 1 clash between Concrete-Rectangular-Column1 [509193/553014] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Floor [490139] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Basic Wall [476476] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Structural Framing [469607] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Ramp [413462/552967] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Shyam Chandresha | Kartik Dalwadi | 2025-10-17 00:00:00 | 2025-10-31 |  |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Shyam Chandresha | 2025-10-18 00:00:00 |  |  |  | 10
#69 | 5 clashes across 2 Clash Groups | Closed | Coordination | Clash | 5 total clashes: 1 clash between Duct [850804] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Pipe [764496] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [520498] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Duct [886404] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Duct [738601] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT | Shyam Chandresha, Kartik Dalwadi | Kartik Dalwadi | 2025-11-15 00:00:00 | 2025-12-23 |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Shyam Chandresha | 2025-11-20 00:00:00 | Kartik Dalwadi | 2025-11-24 00:00:00 |  | 11
#70 | 3 clashes across 2 Clash Groups | Open | Coordination | Clash | 3 total clashes: 1 clash between Concrete-Rectangular Beam1 [476140] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Basic Wall [395400] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [490797/515966] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} |  |  | Tanay Trivedi, Jeffy George MCEM4001 - ICT | Tanay Trivedi | 2025-11-12 00:00:00 | 2025-12-26 |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Kartik Dalwadi | 2025-11-14 00:00:00 |  |  |  | 11
#71 | 24 clashes across 24 Clash Groups | Open | Coordination | Clash | 24 total clashes: 1 clash between Structural Framing [426357] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [401358] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [506668] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Structural Framing [525160] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Ramp [475299/484192] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} | Jeffy George MCEM4001 - ICT | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT | Tanay Trivedi | 2025-11-02 00:00:00 |  | 2025-11-02 |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-11-05 00:00:00 |  |  |  | 11
#72 | Floor [309821] and Basic Wall [398221] | Open | Coordination | Clash | 1 total clashes: 1 clash between Concrete-Rectangular-Column1 [487829/474596] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Tanay Trivedi, Jeffy George MCEM4001 - ICT, Kartik Dalwadi | Kartik Dalwadi | 2025-11-02 00:00:00 |  |  |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Kartik Dalwadi | 2025-11-08 00:00:00 |  |  |  | 11
#73 | 50 clashes across 50 Clash Groups | Open | Coordination | Clash | 50 total clashes: 1 clash between Pipe [824239] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Duct [645475] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Pipe [650009] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [436860] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Structural Framing [484830] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} |  |  | Kartik Dalwadi | Shyam Chandresha | 2025-11-09 00:00:00 | 2025-12-05 | 2025-11-09 |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-11-14 00:00:00 |  |  |  | 11
#74 | Concrete-Rectangular-Column1 [522000/480427] and Concrete-Rectangular Beam1 [506277] | Closed | Coordination | Clash | 1 total clashes: 1 clash between Floor [480955] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Shyam Chandresha | Jeffy George MCEM4001 - ICT | 2025-11-19 00:00:00 |  | 2025-11-19 |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Tanay Trivedi | 2025-11-27 00:00:00 | Tanay Trivedi | 2025-12-14 00:00:00 |  | 11
#75 | 6 clashes across 5 Clash Groups | Open | Coordination | Clash | 6 total clashes: 1 clash between Duct [640948] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [416189/543562] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Ramp [550130/540682] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [443132] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Duct [872808] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT |  | Kartik Dalwadi | 2025-11-20 00:00:00 |  |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-11-29 00:00:00 |  |  |  | 11
#76 | Structural Framing [480784] and Basic Wall [423795] | Open | Coordination | Clash | 1 total clashes: 1 clash between Floor [300790] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} |  |  | Jeffy George MCEM4001 - ICT, Tanay Trivedi | Shyam Chandresha | 2025-11-05 00:00:00 | 2025-11-16 | 2025-11-05 |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-11-06 00:00:00 |  |  |  | 11
#77 | 4 clashes across 1 Clash Groups | Closed | Coordination | Clash | 4 total clashes: 1 clash between Concrete-Rectangular Beam1 [491165] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [446785/540839] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Pipe [877265] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [458376] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Kartik Dalwadi, Jeffy George MCEM4001 - ICT, Tanay Trivedi | Jeffy George MCEM4001 - ICT | 2025-11-16 00:00:00 |  |  |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-11-24 00:00:00 | Shyam Chandresha | 2025-12-04 00:00:00 |  | 11
#78 | 12 clashes across 11 Clash Groups | Open | Coordination | Clash | 12 total clashes: 1 clash between Basic Wall [437031] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Basic Wall [384155] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Basic Wall [425451] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Structural Framing [461430] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Ramp [414796/436735] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT | Shyam Chandresha, Kartik Dalwadi | Tanay Trivedi | 2025-11-24 00:00:00 | 2026-01-03 |  |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Shyam Chandresha | 2025-11-27 00:00:00 |  |  |  | 11
#79 | 10 clashes across 9 Clash Groups | Closed | Coordination | Clash | 10 total clashes: 1 clash between Duct [818274] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Pipe [678233] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Floor [398686] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [541014] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Structural Framing [463168] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT, Tanay Trivedi, Shyam Chandresha | Shyam Chandresha | 2025-11-10 00:00:00 | 2025-11-25 |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Tanay Trivedi | 2025-11-17 00:00:00 | Shyam Chandresha | 2025-12-02 00:00:00 |  | 11
#80 | Ramp [413510/470375] and Pipe [620734] | Closed | Coordination | Clash | 1 total clashes: 1 clash between Concrete-Rectangular-Column1 [449325/554031] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} |  |  | Tanay Trivedi, Jeffy George MCEM4001 - ICT | Shyam Chandresha | 2025-11-09 00:00:00 | 2025-11-23 | 2025-11-09 |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Kartik Dalwadi | 2025-11-13 00:00:00 | Jeffy George MCEM4001 - ICT | 2025-12-04 00:00:00 |  | 11
#81 | 36 clashes across 34 Clash Groups | Open | Coordination | Clash | 36 total clashes: 1 clash between Structural Framing [539893] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Duct [761702] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Floor [394278] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Structural Framing [522160] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [523074/483947] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} | Jeffy George MCEM4001 - ICT | MCEM4001 - ICT | Shyam Chandresha | Shyam Chandresha | 2025-11-25 00:00:00 |  | 2025-11-25 |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Tanay Trivedi | 2025-11-26 00:00:00 |  |  |  | 11
#82 | 2 clashes across 1 Clash Groups | Open | Coordination | Clash | 2 total clashes: 1 clash between Structural Framing [544347] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Duct [734913] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT | Shyam Chandresha | Kartik Dalwadi | 2025-11-19 00:00:00 |  | 2025-11-19 |  |  | CEPT-ICP-M1-STR-MD-19092025.rvt |  | Published | Kartik Dalwadi | 2025-11-28 00:00:00 |  |  |  | 11
#83 | Concrete-Rectangular-Column1 [412717/401673] and Pipe [672085] | Open | Coordination | Clash | 1 total clashes: 1 clash between Ramp [417817/439591] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} | Tanay Trivedi | MCEM4001 - ICT |  | Jeffy George MCEM4001 - ICT | 2025-11-18 00:00:00 | 2025-12-25 | 2025-11-18 |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Shyam Chandresha | 2025-11-28 00:00:00 |  |  |  | 11
#84 | 10 clashes across 9 Clash Groups | Closed | Coordination | Clash | 10 total clashes: 1 clash between Pipe [693987] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [425248/537464] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [463168] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Ramp [562471/538007] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Floor [392914] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} |  |  | Kartik Dalwadi, Tanay Trivedi, Jeffy George MCEM4001 - ICT | Tanay Trivedi | 2025-11-01 00:00:00 |  | 2025-11-01 |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Kartik Dalwadi | 2025-11-05 00:00:00 | Kartik Dalwadi | 2025-11-23 00:00:00 |  | 11
#85 | Pipe [798843] and Pipe [889774] | Open | Coordination | Clash | 1 total clashes: 1 clash between Structural Framing [414710] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} |  |  | Tanay Trivedi, Kartik Dalwadi, Jeffy George MCEM4001 - ICT | Jeffy George MCEM4001 - ICT | 2025-11-03 00:00:00 | 2025-11-24 |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Shyam Chandresha | 2025-11-12 00:00:00 |  |  |  | 11
#86 | 3 clashes across 3 Clash Groups | Open | Coordination | Clash | 3 total clashes: 1 clash between Basic Wall [367016] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Duct [608209] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Ramp [553887/437798] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} |  |  | Kartik Dalwadi | Kartik Dalwadi | 2025-11-28 00:00:00 |  | 2025-11-28 |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-12-07 00:00:00 |  |  |  | 11
#87 | 10 clashes across 5 Clash Groups | Open | Coordination | Clash | 10 total clashes: 1 clash between Duct [807986] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Duct [615532] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Floor [418109] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Structural Framing [459805] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Duct [889951] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} |  |  | Jeffy George MCEM4001 - ICT, Tanay Trivedi, Shyam Chandresha | Kartik Dalwadi | 2025-12-05 00:00:00 | 2025-12-17 |  |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Kartik Dalwadi | 2025-12-09 00:00:00 |  |  |  | 12
#88 | 36 clashes across 31 Clash Groups | Open | Coordination | Clash | 36 total clashes: 1 clash between Basic Wall [567191] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Floor [416584] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Duct [741435] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [434735/422884] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [512978] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} |  |  |  | Kartik Dalwadi | 2025-12-13 00:00:00 | 2026-01-27 | 2025-12-13 |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Kartik Dalwadi | 2025-12-19 00:00:00 |  |  |  | 12
#89 | 5 clashes across 2 Clash Groups | Open | Coordination | Clash | 5 total clashes: 1 clash between Pipe [688867] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [470495] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Floor [370361] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Structural Framing [438255] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [443832/513947] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} |  |  |  | Tanay Trivedi | 2025-12-11 00:00:00 |  |  |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Kartik Dalwadi | 2025-12-17 00:00:00 |  |  |  | 12
#90 | 6 clashes across 4 Clash Groups | Open | Coordination | Clash | 6 total clashes: 1 clash between Duct [799171] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Duct [830803] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Duct [825766] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [478757] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} 1 clash between Duct [705304] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} |  |  | Tanay Trivedi, Shyam Chandresha, Kartik Dalwadi | Kartik Dalwadi | 2025-12-21 00:00:00 | 2026-01-17 |  |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Tanay Trivedi | 2025-12-31 00:00:00 |  |  |  | 12
#91 | 12 clashes across 7 Clash Groups | Open | Coordination | Clash | 12 total clashes: 1 clash between Structural Framing [454958] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Structural Framing [476370] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Concrete-Rectangular-Column1 [507254/530889] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [566025] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Floor [363444] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT |  | Tanay Trivedi | 2025-12-27 00:00:00 | 2026-02-02 | 2025-12-27 |  |  | CEPT-ICP-M1-STR-MD-19092025.rvt |  | Published | Shyam Chandresha | 2026-01-04 00:00:00 |  |  |  | 12
#92 | 10 clashes across 9 Clash Groups | Open | Coordination | Clash | 10 total clashes: 1 clash between Concrete-Rectangular-Column1 [428670/465072] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Duct [687209] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Basic Wall [467644] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Pipe [773852] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Pipe [655545] in CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} |  |  | Kartik Dalwadi | Jeffy George MCEM4001 - ICT | 2025-12-18 00:00:00 |  | 2025-12-18 |  |  | CEPT-ICP-M1-MEP-MD-15092025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-12-24 00:00:00 |  |  |  | 12
#93 | Structural Framing [427406] and Floor [409045] | Open | Coordination | Clash | 1 total clashes: 1 clash between Concrete-Rectangular-Column1 [430426/437139] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Tanay Trivedi, Shyam Chandresha, Jeffy George MCEM4001 - ICT | Tanay Trivedi | 2025-12-19 00:00:00 | 2026-01-23 |  |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Tanay Trivedi | 2025-12-27 00:00:00 |  |  |  | 12
#94 | 24 clashes across 20 Clash Groups | Closed | Coordination | Clash | 24 total clashes: 1 clash between Duct [893522] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Pipe [842249] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Ramp [506180/565087] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [448860] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Pipe [807399] in CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT, Tanay Trivedi, Kartik Dalwadi | Jeffy George MCEM4001 - ICT | 2025-12-10 00:00:00 |  | 2025-12-10 |  |  | CEPT-ICP-M1-ARCH-MD-14092025.rvt |  | Published | Shyam Chandresha | 2025-12-14 00:00:00 | Jeffy George MCEM4001 - ICT | 2026-01-06 00:00:00 |  | 12
#95 | 2 clashes across 2 Clash Groups | Closed | Coordination | Clash | 2 total clashes: 1 clash between Duct [803758] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} 1 clash between Pipe [659890] in CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} | Shyam Chandresha | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT, Tanay Trivedi | Tanay Trivedi | 2025-12-26 00:00:00 |  |  |  |  | CEPT-ICP-M1-STR-MD-19092025.rvt |  | Published | Tanay Trivedi | 2025-12-29 00:00:00 | Shyam Chandresha | 2026-01-03 00:00:00 |  | 12
#96 | 5 clashes across 2 Clash Groups | Closed | Coordination | Clash | 5 total clashes: 1 clash between Structural Framing [566592] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [545467] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [528356] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Floor [336777] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [482465] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} | Jeffy George MCEM4001 - ICT | MCEM4001 - ICT | Shyam Chandresha, Jeffy George MCEM4001 - ICT, Kartik Dalwadi | Kartik Dalwadi | 2025-12-04 00:00:00 | 2026-01-11 |  |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Jeffy George MCEM4001 - ICT | 2025-12-13 00:00:00 | Shyam Chandresha | 2025-12-31 00:00:00 |  | 12
#97 | Concrete-Rectangular-Column1 [548215/408089] and Ramp [476569/408570] | Open | Coordination | Clash | 1 total clashes: 1 clash between Floor [358941] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-MEP-MD-15092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT |  | Tanay Trivedi | 2025-12-16 00:00:00 |  | 2025-12-16 |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Shyam Chandresha | 2025-12-26 00:00:00 |  |  |  | 12
#98 | 50 clashes across 50 Clash Groups | Open | Coordination | Clash | 50 total clashes: 1 clash between Ramp [478042/408449] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Structural Framing [468895] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Duct [645604] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Structural Framing [430772] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} 1 clash between Ramp [455018/554120] in CEPT-ICP-M1-Coordinated-MD-07082025.rvt - {3D} and CEPT-ICP-M1-ARCH-MD-14092025.rvt - {3D} |  |  | Shyam Chandresha | Tanay Trivedi | 2025-12-27 00:00:00 | 2026-02-08 |  |  |  | CEPT-ICP-M1-Coordinated-MD-07082025.rvt |  | Published | Kartik Dalwadi | 2025-12-31 00:00:00 |  |  |  | 12
#99 | 36 clashes across 36 Clash Groups | Open | Coordination | Clash | 36 total clashes: 1 clash between Concrete-Rectangular-Column1 [435543/507897] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Basic Wall [392698] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Concrete-Rectangular Beam1 [434784] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Ramp [438336/484435] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Ramp [502944/528308] in CEPT-ICP-M1-STR-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT, Tanay Trivedi, Kartik Dalwadi | Shyam Chandresha | 2025-12-09 00:00:00 | 2026-01-02 | 2025-12-09 |  |  | CEPT-ICP-M1-STR-MD-23082025.rvt |  | Published | Tanay Trivedi | 2025-12-16 00:00:00 |  |  |  | 12
#100 | 12 clashes across 12 Clash Groups | Open | Coordination | Clash | 12 total clashes: 1 clash between Duct [633203] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Pipe [714205] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Pipe [711071] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Structural Framing [470395] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} 1 clash between Duct [748684] in CEPT-ICP-M1-Coordinated-MD-23082025.rvt - {3D} and CEPT-ICP-M1-STR-MD-19092025.rvt - {3D} | Kartik Dalwadi | MCEM4001 - ICT | Jeffy George MCEM4001 - ICT, Kartik Dalwadi | Tanay Trivedi | 2025-12-12 00:00:00 | 2026-01-17 |  |  |  | CEPT-ICP-M1-Coordinated-MD-23082025.rvt |  | Published | Shyam Chandresha | 2025-12-14 00:00:00 |  |  |  | 12

## Scenarios
Scenario_ID | Scenario_Name | Resolution_Rate | New_Issues_Rate | Coordination_Quality | Error_Discovery_Rate | Stage_Gate_Compliance | Description
S1 | Low Coordination | 0.3 | 3 | 0.2 | 0.1 | 0 | High clash environment
S2 | Moderate Coordination | 0.5 | 2 | 0.5 | 0.4 | 0.5 | Improved coordination
S3 | BIM + LLM | 0.7 | 1 | 0.8 | 0.7 | 1 | Optimized workflow

## Simulation_Output
Scenario_ID | Time | Open_Issues | Rework
S1 | 1 | 4.98 | 1
S1 | 2 | 4.96 | 2
S1 | 3 | 4.94 | 3
S1 | 4 | 4.92 | 4
S1 | 5 | 4.9 | 5
S1 | 6 | 4.88 | 6
S1 | 7 | 4.86 | 7
S1 | 8 | 4.84 | 8
S1 | 9 | 4.82 | 9
S1 | 10 | 4.8 | 10
S1 | 11 | 4.78 | 11
S1 | 12 | 4.76 | 12
S1 | 13 | 4.74 | 13
S1 | 14 | 4.72 | 14
S1 | 15 | 4.7 | 15
S1 | 16 | 4.68 | 16
S1 | 17 | 4.66 | 17
S1 | 18 | 4.64 | 18
S1 | 19 | 4.62 | 19
S1 | 20 | 4.6 | 20
S1 | 21 | 4.58 | 21
S1 | 22 | 4.56 | 22
S1 | 23 | 4.54 | 23
S1 | 24 | 4.52 | 24
S1 | 25 | 4.5 | 25
S1 | 26 | 4.49 | 26
S1 | 27 | 4.47 | 27
S1 | 28 | 4.45 | 28
S1 | 29 | 4.43 | 29
S1 | 30 | 4.41 | 30
S1 | 31 | 4.39 | 31
S1 | 32 | 4.37 | 32
S1 | 33 | 4.35 | 33
S1 | 34 | 4.33 | 34
S1 | 35 | 4.31 | 35
S1 | 36 | 4.29 | 36
S1 | 37 | 4.27 | 37
S1 | 38 | 4.25 | 38
S1 | 39 | 4.23 | 39
S1 | 40 | 4.21 | 40
S1 | 41 | 4.19 | 41
S1 | 42 | 4.17 | 42
S1 | 43 | 4.15 | 43
S1 | 44 | 4.13 | 44
S1 | 45 | 4.11 | 45
S1 | 46 | 4.09 | 46
S1 | 47 | 4.07 | 47
S1 | 48 | 4.05 | 48
S1 | 49 | 4.03 | 49
S1 | 50 | 4.01 | 50
S2 | 1 | 3.94 | 0.36
S2 | 2 | 3.88 | 0.72
S2 | 3 | 3.82 | 1.08
S2 | 4 | 3.76 | 1.44
S2 | 5 | 3.7 | 1.8
S2 | 6 | 3.64 | 2.16
S2 | 7 | 3.58 | 2.52
S2 | 8 | 3.52 | 2.88
S2 | 9 | 3.46 | 3.24
S2 | 10 | 3.4 | 3.6
S2 | 11 | 3.34 | 3.96
S2 | 12 | 3.28 | 4.32
S2 | 13 | 3.22 | 4.68
S2 | 14 | 3.16 | 5.04
S2 | 15 | 3.1 | 5.4
S2 | 16 | 3.04 | 5.76
S2 | 17 | 2.98 | 6.12
S2 | 18 | 2.92 | 6.48
S2 | 19 | 2.86 | 6.84
S2 | 20 | 2.8 | 7.2
S2 | 21 | 2.74 | 7.56
S2 | 22 | 2.68 | 7.92
S2 | 23 | 2.62 | 8.28
S2 | 24 | 2.56 | 8.64
S2 | 25 | 2.5 | 9
S2 | 26 | 2.44 | 9.36
S2 | 27 | 2.38 | 9.72
S2 | 28 | 2.32 | 10.08
S2 | 29 | 2.26 | 10.44
S2 | 30 | 2.2 | 10.8
S2 | 31 | 2.14 | 11.16
S2 | 32 | 2.08 | 11.52
S2 | 33 | 2.02 | 11.88
S2 | 34 | 1.96 | 12.24
S2 | 35 | 1.9 | 12.6
S2 | 36 | 1.84 | 12.96
S2 | 37 | 1.78 | 13.32
S2 | 38 | 1.72 | 13.68
S2 | 39 | 1.66 | 14.04
S2 | 40 | 1.6 | 14.4
S2 | 41 | 1.54 | 14.76
S2 | 42 | 1.48 | 15.12
S2 | 43 | 1.42 | 15.48
S2 | 44 | 1.36 | 15.84
S2 | 45 | 1.3 | 16.2
S2 | 46 | 1.24 | 16.56
S2 | 47 | 1.18 | 16.92
S2 | 48 | 1.12 | 17.28
S2 | 49 | 1.06 | 17.64
S2 | 50 | 1 | 18
S3 | 1 | 2.9 | 0.12
S3 | 2 | 2.8 | 0.24
S3 | 3 | 2.7 | 0.36
S3 | 4 | 2.6 | 0.48
S3 | 5 | 2.5 | 0.6
S3 | 6 | 2.4 | 0.72
S3 | 7 | 2.3 | 0.84
S3 | 8 | 2.2 | 0.96
S3 | 9 | 2.1 | 1.08
S3 | 10 | 2 | 1.2
S3 | 11 | 1.9 | 1.32
S3 | 12 | 1.8 | 1.44
S3 | 13 | 1.7 | 1.56
S3 | 14 | 1.6 | 1.68
S3 | 15 | 1.5 | 1.8
S3 | 16 | 1.4 | 1.92
S3 | 17 | 1.3 | 2.04
S3 | 18 | 1.2 | 2.16
S3 | 19 | 1.1 | 2.28
S3 | 20 | 1 | 2.4
S3 | 21 | 0.9 | 2.52
S3 | 22 | 0.8 | 2.64
S3 | 23 | 0.7 | 2.76
S3 | 24 | 0.6 | 2.88
S3 | 25 | 0.5 | 3
S3 | 26 | 0.4 | 3.12
S3 | 27 | 0.3 | 3.24
S3 | 28 | 0.2 | 3.36
S3 | 29 | 0.1 | 3.48
S3 | 30 | 0 | 3.6
S3 | 31 | 0 | 3.72
S3 | 32 | 0 | 3.84
S3 | 33 | 0 | 3.96
S3 | 34 | 0 | 4.08
S3 | 35 | 0 | 4.2
S3 | 36 | 0 | 4.32
S3 | 37 | 0 | 4.44
S3 | 38 | 0 | 4.56
S3 | 39 | 0 | 4.68
S3 | 40 | 0 | 4.8
S3 | 41 | 0 | 4.92
S3 | 42 | 0 | 5.04
S3 | 43 | 0 | 5.16
S3 | 44 | 0 | 5.28
S3 | 45 | 0 | 5.4
S3 | 46 | 0 | 5.52
S3 | 47 | 0 | 5.64
S3 | 48 | 0 | 5.76
S3 | 49 | 0 | 5.88
S3 | 50 | 0 | 6

## SD_Parameters
SD_Parameter | RII_Challenge | RII_Score | Weight | S1_Value | S2_Value | S3_Value
New_Issues_Rate | Unclear client requirements | 0.875 | 0.205 | 3 | 2 | 1
Coordination_Quality | BIM used as drafting tool | 0.85 | 0.199 | 0.2 | 0.5 | 0.8
Error_Discovery_Rate | Rework due to unidentified design issues | 0.85 | 0.199 | 0.1 | 0.4 | 0.7
Resolution_Rate | Poor coordination between disciplines | 0.85 | 0.199 | 0.3 | 0.5 | 0.7
Stage_Gate_Compliance | Late stakeholder input (Freq RII) | 0.842 | 0.197 | 0 | 0.5 | 1
Note: Weight = RII Score / Sum of all RII scores (4.267). Parameters derived from DRP survey (n=24).